## Slide 1
Report to the Human Settlements Portfolio Committee
A report detailing the plan of action regarding the challenges of the Rocky Park project
11 August 2026
Inspiring Hope for a Better Future
Umuntu Ngumuntu Ngekhaya

## Slide 2: CONTENTS
TITLE
Inspiring Hope for a Better Future
Umuntu Ngumuntu Ngekhaya
1. Background
2. Discussion of Current Status of the Rocky Park Project
3. Progress Made
4. Way Forward

## Slide 3: 1. BACKGROUND
TITLE
Inspiring Hope for a Better Future
Umuntu Ngumuntu Ngekhaya
The Rocky Park project located in KwaDukuza Municipality has been plagued by many challenges including disputes with the previous service provider, delays in completion, multiple audits and invasion of units.
There are currently two groups of occupiers of the units. The first is legal occupiers namely persons who have lease agreements with the municipality and the second group is comprised of persons who illegally invaded units.
The project is located on land owned by the municipality.

## Slide 4: 2. DISCUSSION ON CURRENT STATUS OF THE ROCKY PARK PROJECT
TITLE
Inspiring Hope for a Better Future
Umuntu Ngumuntu Ngekhaya
A cabinet decision was taken during 2024 for the Department of Human Settlements (Province) to take over the Developer status and the project.
To address the challenges and to move forward with finalizing the project the following activities needed to be finalized: -
Completion of a structural assessment of the completed units
Eviction of the illegal occupiers
Province and the KwaDukuza Municipality established a joint task team and Province attended to consultations and assisted the municipality’s legal team with preparing the eviction application papers.
It was established that moving forward it was critical to obtain vacant possession so that the units could be correctly allocated.
The audit processes were completed, and the Municipality was tasked as the landowner with bringing the eviction application. Province is working closely with the Municipality to overcome the challenges. Since the land is owned and managed by the Municipality ultimately, they will need to initiate the necessary processes to overcome the challenges.

## Slide 5
TITLE
Inspiring Hope for a Better Future
Umuntu Ngumuntu Ngekhaya
A meeting was held on the 31 January 2025 attended by Province and municipal officials in which the following was discussed: -
The slow progress in finalizing and setting down the eviction applications
The municipality acknowledged that delays were experienced due to misplaced /records and challenges in identification of occupiers.
The meeting resolved that: -
Municipality will lodge an application to court by 14 February 2025. A copy of the papers to be sent to Director; Legal Services KZN Human Settlements before lodgment for perusal.
The date the matter will be heard is up to the court but will be communicated with all parties.
Municipality will give a written report outlining the progress made and regular. Meetings will take place to discuss progress.
The Provincial Cabinet will be updated on all developments

## Slide 6: 3. Progress Made
TITLE
Inspiring Hope for a Better Future
Umuntu Ngumuntu Ngekhaya
Municipality lodged an application to compel the occupants to comply with its request to be profiled which is necessary prior to its consideration of an eviction.
The rule nisi was granted on 11th June 2025 thereby:
authorizing the Applicant, together with members of the SAPS, private security, and the Sheriff, to access the Rocky Park Integrated Residential Development, including residential units in apartment block C to H and J, irrespective of occupancy.
The occupants are directed to allow such access and to reasonably cooperate by providing information relation to their identity and personal circumstances to assist the Applicant in determining their legal status.
Provision was made for substituted service through publication in local newspapers and notices placed at the entrances of the relevant apartment blocks. Furthermore, the occupants are authorized to attend the Applicant’s offices to furnish the required information.

## Slide 7: 3. Progress Made
TITLE
Inspiring Hope for a Better Future
Umuntu Ngumuntu Ngekhaya
On the return court date being the 15th of August 2025, the interim order as stated above was confirmed with the following additional orders, that:
  the Municipality with the assistance of SAPS is to protect and ensure the protection of the rights of the First Respondent in its execution of the Rule, including but not limited to, not removing, confiscating or damaging any movable property of the First Respondent during the verification process
  The Applicant is directed not to evict the First Respondent without a Court Order
  The municipality reported that it is currently working with SAPS and their internal security unit to finalize plans to accompany and support the relevant staff members who will be undertaking the socio-economic survey.
  The Department will continue to monitor and report in respect of progress made.
  The Department will assist the municipality in respect of the next step which is the eviction process.
.

## Slide 8: 4. Way Forward
TITLE
Inspiring Hope for a Better Future
Umuntu Ngumuntu Ngekhaya
Despite numerous follow-ups made to the municipality. The municipality has failed to take the appropriate steps and ignored all meeting requests.
The Department addressed correspondence to the Municipality on 05 August 2026 requesting further updates on the Rocky Park matter. The Department has also invited the Municipality to attend the meeting scheduled for 11 August 2026.
The Municipality advised the Department on 07 August 2026 that they will not be able to attend the meeting scheduled for 11 August 2026 due to prior commitments. The Municipality undertook to meet with the Department and further provide the Department with a progress report.
The Department will endeavor to schedule a meeting with the Municipality to discuss progress on the matter.
.

## Slide 9
THANK YOU
(031) 336 5300 (dbn)
Kwazulu-Natal Department of Human Settlements
www.kzndhs.gov.za
@kzndohs
0800 701 701
ANTI-FRAUD E-MAIL:
fraudhotline@kzndhs.gov.za
(033) 392 6400 (pmb)
@kzn.humansettlements
Inspiring Hope for a Better Future
Umuntu Ngumuntu Ngekhaya